## Sheet1
Name | Batch
Dendayal Kumawat | Spic 5
Date | Assign Task | Completed task | Remark
2016-11-21 | Struts HyperLink,Search Data Using Id | Struts Hyperlink | Due to server problem and slow pc
| and name |  | I didn't complete this task todays
2016-11-22 | Search Data Using Id | complete | complete
2016-11-23 | Login Page | Code Complete | Connection Not Established
2016-11-24 | Login Page and Name wise data fetch from database | Code Complete | due server side vaildation bcz no more time remaining
2016-11-25 | login validation and successfully login,project manger | Code Complete
register and insert data from database
2016-11-26 | Saturday
2016-11-27 | Sunday
2016-11-28 | project manger register and login | code Complete
2016-11-29 | Admin Login,Admin Add Project manger and Intern | code Complete
| Admin See all project mangers details | code Complete
| Project manger fetch data using by id and update | procssing | time
2016-11-30 | " ",inetrn login register by admin intern data fetch and
Intern fetch data by id and update their profile
| project manger add group | procssing | error
2016-12-01 | project manger add batch,add group | complete
2016-12-02 | leave
2016-12-03 | Saturday
2016-12-04 | Sunday
2016-12-05 | add group and assign project
2016-12-06 | phone book project save fetch data | complete
2016-12-07 | search by name and mobile no, and delete by id | complete
2016-12-08 | update | incomplete | TLD file error in web xml,servlet,el language mapping
code is corret
2016-12-09 | add group | complete
2016-12-10 | add group and update forigen key in intern table | code complete | error when update foreign key in intern table
2016-12-11 | Sunday
2016-12-12 | correct error of group and create group leader | code Complete
2016-12-13 | " " | complete
2016-12-14 | create Assign project page | complete
15-12-2016 | view page project assign | complete
16-12-2016 | add project task using Ajax | code complete
17-12-2016 | saturday
18-12-2016 | Sunday
19-12-2016 | view page of assign project task and intern change status | procssing | error occurred due json configration in struts.xml
| and project manger can see project status |  | not completed
20-12-2016 | Exam module create and View | comleted
21-12-2016 | add exam question by id and view part(leave)
22-12-2016 | Job Fair
23-12-2016 | Sql Joins
24-12-2016 | Eaxm module add question by id
25-12-2016 | Sunday
26-12-2016 | Add new Exam question | processing | error Null pointer
27-12-2016 | " " New Exam question View Part,and
| view questions using by exam id | completed
28-12-2016 | delete question using question Id | Processing
29-12-2016
30-12-2016
31-12-2016